## Sheet1
Hardware interface and Reliability package | Understanding the system (mechanical, electrical and logical objects) Ensuring interdependence between mechanical components (servo motor, differential, cogwheels, shaft) | Understanding and Conducting the process of Calibration Adjusting the position and orientation of the Camera | Identifying noise/vibration in system Mitigation through testing, active or passive control | Debbuging Ensuring proper functioning of the system Stable connection between all components
Embedded platform and Software architecture package | Attended the seminars about Brain and Embedded platform Understanding interconnection between RaspberryPi and Nucleo Understanding Inter Process Communication workflow | Implementing simple real-time image analisys functionality | Developing stable and responsive real-time image processing | Verification of system Responsiveness Ensuring proper process communication | Reliability and Optimisation
Virtual Verification package | Early environment setup Simulator verification first approach | Simulator first validation approach Understanding Simulator - Reality mismatch Measuring Sim-to-Real gap
Controlled Driving package |  | Development of software support for simple vehicle movement | Use for debugging purposes Checking validity of movement operations
Autonomous Driving package | Developed simple lane recognition algorithm | Connecting algorithm with the Brain Embedded platform Calibrating the algorithm for testing environment Simple road object recognition algorithm | Stable autonomous behaviour in controlled scenarios Improved sign and traffic signalisation recognition | Performance verification, Robustness, Edge cases | Reliability and Optimisation
Deadlines | 22. dec 2025. | 2. feb 2026. | 9. mar 2026. | 13. apr 2026. | 16 - 20. may 2026.